## Sheet1
[8 empty] | QA Status |  | Developer Status | QA Status
Id | Title | Description | Video for reference url | Browser | Version | Severity | occurrence | Status(27/08//2015) | Status(02/09/2015) | Status(02/09/2015) | Status(08/092015) | suggetion
1 | Help on Configure Control page is not working. | Go to Home > Security Control > Configure Control. Click on Help Icon. Expected behaviour: Help popup should open. Actual Behaviour : Help popup is not being opened. | http://screencast.com/t/Vol8a9OxIeIp | Firefox 40.0.2 |  | Critical | always |  | Help page is opens with invalid content |  | Help page is opens with invalid content
2 | Mouse click in not working while selecting control name on new control screen. | Go to Home > Security Control > Configure Control. Click on "New Control" button. Type "Quick". It will show a list of related options. Try to select one of them through mouse. Expected behaviour: Data should be selected. Actual Behaviour : Data is not being selected. Note: Same is working fine when we select from keyboard. | http://screencast.com/t/wU7uxFiyL | Firefox 40.0.2 |  | Low | always | Verified | verified |  | Still mouse click in not working
3 | Window title for "New Control" should be changed. | Go to Home > Security Control > Configure Control. Click on "New Control" button. Currently Title is "Edit Review/Update Control Screen". It should be something like : "New/Add Control". | http://screencast.com/t/ar1U7LrPSZI | Firefox 40.0.2 |  | Medium | always |  |  |  | Title is not proper. There should be create and update control screen.
4 | Decimal Constraint error should there for port value on configure control | Go to Home > Security Control > Configure Control. Click on "edit" in any row of grid give decimal value in port text box Expected behaviour: Error message for decimal value. Current behaviour: no error message of data constraint Note:- error message occurs accept "." although update is also not performing for that reason. | http://screencast.com/t/ScKcto1h | Firefox 40.0.2 |  | Medium | always |  |  |  | Still reproducing , Unable to save control
5 | Null is displaying in grid for the blank value for port and process name on Control configure | Go to Home > Security Control > Configure Control. Click on "New Control" button. Give blank entry in process name and click save Expected behaviour: error message should be there or if blank value accepted then it should be blank in the grid view Current behaviour: it is taking "NULL" value and same is displaying in Grid. | http://screencast.com/t/SecB3zbME3c | Firefox 40.0.2 |  | Critical | always |  | save button not woking to check this issue
6 | Mandatory fields should be remarked with * in front of input box | Suggestion: we should mark * symbol in front of necessary fields value. |  |  |  | Medium | always | partialy fixed | partialy fixed |  | partialy fixed
7 | Sorting on the grid on the basis of certain column is not functioning | Go to Home > Security Control > Configure Control. Perform some deletion operation or add new control then try to sort the data for certain column sorting is not performing Expected behaviour: Sorting should be performed. | http://screencast.com/t/k5S4dxMU3l1T | Firefox 40.0.2 |  | Low | sometime | Verified | verified |  | verified
8 | No special characters are allowed in the control name | Go to Home > Security Control > Configure Control. Click on "New Control" button. Give control name as a special character string like"-------". Expected behaviour:- proper message of constraint current behaviour: accepting special characters as control name. Note:- name should start with alphabet. | http://screencast.com/t/oq6Gftfd4dC | Firefox 40.0.2 |  | Low | always |  |  | Done | verified | there should be proper messege like:" 1.Control name contains alphabates only" 2.Control name contains alphabanumeric value only 3.Control name should not contain specail character
9 | Limitation of text typing | Suggestion: there should be limitation of text. For example: port number should be of 4-5 digit only or control name should not be of 50 characters "Port numbers are from 0 to 65535. Ports 0 to 1024 are reserved for use by certain privileged services." |  | Firefox 40.0.2 |  | Low | always |  |  | Done | pending due to save button not working
10 | Update is not working when we left blank entry in process name. | Go to Home > Security Control > Configure Control. Click on "edit" in any row of grid make a blank entry in process name Expected behaviour:- if port number is then update should be working fine. | http://screencast.com/t/jZCLhT008V | Firefox 40.0.2 |  | Medium | always | Verified | verified
11 | Show entries and search values are persisting even when we re direct/comes from other page | Go to Home > Security Control > Configure Control select 10 in combo box of "Show Entries" or search text "abc" Now click on any different page and come again to these page. Expected behaviour: values must be re initialised to the default either the result also persist to the same state. Current behaviour: values are not persisting as per search result. | http://screencast.com/t/e244vVW6HpDf http://screencast.com/t/qMCHbCDrn | Firefox 40.0.2 |  | Medium | always
12 | Save is not working when we add a new control with port and process name. | Go to Home > Security Control > Configure Control. Click on "New Control" button. Giving port and process name the save button is not functioning Expected Behaviour: either give proper message or saving should be performed. | http://screencast.com/t/NRAsl0RJa | Firefox 40.0.2 |  | Critical | always | sometime works | sometime works |  | sometime works
13 | No proper message for same control name while saving | Go to Home > Security Control > Configure Control. Click on "New Control" button. Give same name of control same as previous ones. Expected behaviour: error message should be saved. Current behaviour: save button is not performing any thing. | http://screencast.com/t/5InFk4RKITo | Firefox 40.0.2 |  | Low | always | Verified | Verified |  | Verified
14 | Check boxes should be disable and display there value as per database in the grid. | Go to Home > Security Control > Configure Control Deployment. View monitor status and monitor performance in grid view. Expected behaviour: Check boxes will be disable and should reflect as per database value. Current behaviour: checkbox is enable. | http://screencast.com/t/ctyDUBq6f | Firefox 40.0.2 |  | Low | always
15 | Select <field name> should not be option in combo box list. | Suggestion: every combo box contacting the message of selecting the item list. It should either be blank or on clicking combo button these message should not be the part of option. | http://screencast.com/t/mZObeNDxXDxT | Firefox 40.0.2 |  | Low | always
16 | Control name should be combo box as it is previously defined in configure Control. | Go to Home > Security Control > Configure Control Deployment. New Control Deployment the control name value should be selected from combo box rather than the text box. | http://screencast.com/t/pTAFhKqh | Firefox 40.0.2 |  | Critical | always
17 | No error message for different control name while saving and save button also not functioning | Go to Home > Security Control > Configure Control Deployment Click on "New Control Deployment" button. Giving different name other than existing name the save button is not functioning and no message for the same. Expected Behaviour: either give proper message or saving should be performed. | http://screencast.com/t/V8hXYf1tAP | Firefox 40.0.2 |  | Critical | always
18 | Update is not working when we select or de select from tree view | Go to Home > Risk Assessment> Configure select or de select from tree view click on update button. Expected behaviour: The tree view should be updated. Current behaviour: it is not updated and not display of updated values in tree view | http://screencast.com/t/kRtsLfFk | Firefox 40.0.2 |  | Critical | many times | inconsistent behaviour |  |  | inconsistent behavior
19 | On adding a sibling in tree view with special characters that tree becomes disappear | Go to Home > Risk Assessment> Configure select a folder and right click for add a sibling with name contains special characters "~!@#" click on save. After that tree view is disappeared. |  | Firefox 40.0.2 |  | Critical |  | inconsistent behaviour
20 | Slow response of ontology tree | Go to Home > Risk Assessment> Configure |  | Firefox 40.0.2 |  | Critical | many times | inconsistent behaviour |  |  | verified
21 | We are not able to assign a security control to any folder | Go to Home > Risk Assessment> Configure select a folder and right click for add a security control. Popup appears but there is no option for select the control name. | http://screencast.com/t/enKXctjRbB | Firefox 40.0.2 |  | Critical |  | inconsistent behaviour
22 | Enter Key is not working at many place | Go to Home > Risk Assessment> Configure select a folder and right click for add a child popup appears for taking input give the proper input and try to save with pressing enter key |  | Firefox 40.0.2 |  | low |  | inconsistent behaviour |  |  | inconsistent behaviour
23 | Option for "Select All" should be available for select/deselect all the items(Security Control). | Go to Home > Risk Assessment> Configure select a folder and right click for add a security control. There is no option for selecting or de selecting all items. | http://screencast.com/t/HJLr7XiqVp9 | Firefox 40.0.2 |  | Low |  | inconsistent behaviour
24 | Update risk configure functioning slow. | Go to Home > Risk Assessment> Configure Select or de select from tree view click on update button. Slow response and not proper message for the process is still performing. | http://screencast.com/t/p0xSo0X1r0k | Firefox 40.0.2 |  | Low |  | inconsistent behaviour
25 | User is not able to recognize that update is in process or it is completed.(We should have loading image till update is performing.) | Go to Home > Risk Assessment> Configure Select or de select from tree view click on update button. Slow response and not proper message for the process is still performing. |  | Firefox 40.0.2 |  | Low |  | inconsistent behaviour
26 | Website becomes unresponsive sometimes. | Work on the project some times it do not behave any thing and become dump or unresponsive. | http://screencast.com/t/mYWmzCYlvvF | Firefox 40.0.2 |  | Low |  | inconsistent behaviour
27 | There should be proper name for tab1 and tab2 | Home>Risk Assessment>Grid look tab1 and tab2 note: instead of tab1 there should be name "Risk" instead of tab2 there should be name "Security control" | http://screencast.com/t/52yWVBe9D | Firefox 40.0.2 |  | Medium
28 | grid view should have relevant name | Home>Risk Assessment note: there should be name like "Risk and security control tropical terms" |  |  |  | Medium
29 | blank list opens for security control to any folder on risk assessment>configure | Home>Risk Assessment>configure click any folder from tree view right click for give security control we get popup for proving security control blank list is appearing | http://screencast.com/t/xckTcfcCW5Y | Firefox 40.0.2 |  | Medium |  | inconsistent behaviour
30 | Taking long time for tree view and making update on it. | Home>Risk assessment> configure while clicking on configure it takes long time for fetching the tree view and while making an update on tree folder it will again take long wait and even some times hang. |  |  |  | Critical |  | inconsistent behaviour
31 | Tree view is not view in always sequence | Home>Risk Assessment>configure tree view (sequence of folder) are disarrange on every time we go on it. it should be alphabetic or same as the previous one |  |  |  | Medium |  | inconsistent behaviour
32 | Alert ignore and restart button is not working | Home>Alerts>Review Alerts on clicking ignore button it should ignore the alert on clicking restart button it should restart the alert |  |  |  | Critical |  | there is no data in database to check the issue
34 | Session is maintained even though we close the browser | Home note: for security purpose session should not be maintain when we close the browser. |  |  |  | Medium
35 | wrong userid/password message is not in proper format | home>login if give wrong userid or password it will show the wrong userid message which should be in red font and in proper format. |  |  |  | Critical |  |  | verified
36 | Option will disable or there should different form for login | If we not login from home page we are able to view all option. Note:- either disable all the option until valid login will not perform or give different login form. |  |  |  | Critical |  |  | verified
37 | wrong userid/password message is missing | home>login if give wrong userid or password it should prompt for invalid userid or password. |  |  |  | Medium |  |  | verified
38 | While we make update it shows updated result but while clicking on notification column for sorting it will give previous value | Home> Alerts>Configure click any row for edit make a change in notification click update updated result and message are viewed on page now click on the notification column title for sorting you will find the previous value before updated again edit the record but here you find updated value | http://screencast.com/t/LnSf9kXfujzW |  |  | Critical |  |  | verified
39 | Title of the popup screens are not up to the mark | At some where title of the popup screens are not relevant or not proper 1. Home>Alerts>Configure>new alert the popup title is "Edit/New Configure Screen" it may be "New Alert Configure" 2. Home>Security control>configure control>new control the popup tiltle is "Create Review/Update Control Screen" it may be "Add New Control" 3. Home>Security control>configure control deployment the popup title is "Security Control Screen" it may be"Add New Control Deployment" |  |  |  | Medium
40 | There is not relevant comments at front of text boxes | Home>Security Control>Configure controls click on new control there is unwanted or not relevant message in the front of control name text box("Create new control. Dropdown is for suggestion.") | http://screencast.com/t/lqHCjushKNrU |  |  | Critical |  |  | verified
41 | There is no message for session expired | Not active user after 30 min. there should be session out as well as session expired message will be there. even though when session out then there should be message. |  |  |  | Medium
42 | little blink on login page | not proper behaviour | http://screencast.com/t/TVtOcss9 |  |  | Low
43 | delete on action for control is not working | Home>Security Control>Configure Controls when deletion is performing in the action its giving "Control Monitor Deleted Successfuly" but there is no record deleted from the view | http://screencast.com/t/gFv6p5k7
new issues on/after 8th sep 2015
44 | Save button sometime working while process name is blank | Home>Security Control>Configure Controls>new control when we are clicking on save button sometimes its not working but something there is process name blank after that "save" working
45 | Junk Popup window open while performing editing on process name | Home>Security Control>Configure Controls>Edit when we edit "quick heal total security 23" row, then we are giving alphanumeric value such as "lmn@125" then junk popup window open there. | http://screencast.com/t/mqZfcSLcV
46 | Update is not working. | Home>Security Control>Configure Controls>Edit when we change the process name and try to update the value then it is not working.
47 | Browser hangs on performing operations. Sometimes it is slower litle bit more than expected. |  | http://screencast.com/t/lkAkocOu
48 | Misbehaving click operation on tree heirarchy for Risk Analysis > Configure |  | http://screencast.com/t/hR4M3tN5